## deneme
Task Name | Duration | Predecessors | Start | Finish | Resource Names
Analyze requirements | 10 |  | 2017-10-14 | 2017-10-24 | Berkay , Can , Abdulwahab , İlkay
Project Planning | 3 | 1 | 2017-10-24 | 2017-10-27 | Berkay , Can , Abdulwahab , İlkay
Scenario writing | 7 | 2 | 2017-10-25 | 2017-11-01 | Berkay, Abdulwahab , İlkay
Gather components | 2 | 2 | 2017-10-29 | 2017-10-31 | Berkay, Can
Prepare RAD document | 21 | 2 | 2017-10-28 | 2017-11-17 | Berkay , Can , Abdulwahab , İlkay
Redesign existing Components | 9 | 3.4 | 2017-10-31 | 2017-11-08 | Berkay , Can , Abdulwahab , İlkay
Use Case diagram | 1 |  | 2017-10-31 | 2017-11-01 | Abdulwahab
Sequence Diagram | 3 |  | 2017-11-05 | 2017-11-08 | Can
Class Diagram | 1 |  | 2017-11-07 | 2017-11-08 | Berkay
System Requirement controll | 4 | 6 | 2017-11-08 | 2017-11-12 | Berkay , Can , Abdulwahab , İlkay
Fix | 4 | 10 | 2017-11-12 | 2017-11-16 | Berkay , Can , Abdulwahab , İlkay
Implementation | 30 | 11 | 2017-11-16 | 2017-12-16 | Berkay , Can , Abdulwahab , İlkay
Development | 20 |  | 2017-11-16 | 2017-12-06 | Berkay, Can , İlkay
Setting up enviroment | 3 |  | 2017-12-06 | 2017-12-09 | Abdulwahab
Alpha Test/Quality Test | 7 |  | 2017-12-09 | 2017-12-16 | Berkay , Can , Abdulwahab , İlkay
Deployment | 10 | 12 | 2017-12-16 | 2017-12-26 | Berkay
Beta Test | 5 |  | 2017-12-16 | 2017-12-21 | Can , İlkay , Abdulwahab
Setup production | 5 |  | 2017-12-21 | 2017-12-26 | Berkay , Can , Abdulwahab , İlkay
Release | 1 | 16 | 2017-12-26 | 2017-12-27 | Berkay , Can , Abdulwahab , İlkay